## Sheet1
Risk ID | Risk Description | Project Stage | Project Category | Risk Owner | Mitigating Action | Likelihood (1-10) | Impact (1-10) | Risk Priority (low, med, high)
R1 | Opening of the Moorgate Crossrail station is delayed further. | Operational | Operational | Unknown | Regular engagement with Crossrail from now to 2020/2021 to allow for alternative arrangements to be made should there be a delay. | 4 | 3 | Low
R2 | The Riney highways contract expires in summer 2022, and any slippage in starting the construction programme may necessitate finding a new Principal Contractor for the later delivery stages. | Construction | Operational | Unknown | Discussions to take place internally should this risk look more probable on how work would be transferred to a new contractor. | 3 | 4 | Low
R3 | Delays to the four developments surrounding the Moorgate Crossrail station delay the final delivery phases of the MCSL project. | Construction | Operational | Unknown | Regular engagement with developers from now until completion to allow for alternative arrangements if delays occur and to ensure early awareness of any issues. | 5 | 7 | Med
R4 | Infrastructure and utilities difficulties at the Moorgate junction with London Wall and Ropemaker Street make it difficult or too expensive to design and transform the space, as well as enhance safety. | Construction | Technical | Unknown | Set expectations early when major physical constraints are discovered and work closely with internal and external stakeholders to identify design solutions that may not require extensive physical changes. | 5 | 8 | High
R5 | Key stakeholder(s) do not endorse design options. | Planning | Operational | Unknown | Ensure that the Stakeholder Working Group is suitably engaged and that design options are presented with clear rationale to secure endorsement. | 5 | 7 | Med
R6 | Delays or changes to dependency projects, such as Beech Street and St. Paul's Gyratory. | Planning | Operational | Unknown | Work with internal stakeholders to minimize any impacts should changes arise. | 5 | 7 | Med
R7 | Breakdown in engagement with key stakeholders, such as Islington Council. | Planning | Operational | Unknown | Ensure coherent communications with stakeholders at strategic points throughout the project, particularly regarding proposed boundary solutions. | 3 | 7 | Low
R8 | TfL restructure may mean that no dedicated scheme sponsor or resource can be allocated to progress any required TfL approvals. | Planning | Operational | Scheme Sponsor | Officers will seek to establish resources early, maintain close contact to understand the restructure, and seek reassurance of resource if needed. | 8 | 8 | High
R9 | The proposed scheme could negatively impact protected characteristics under the Equalities Act 2010. | Planning | Legislation | Unknown | Meetings with representative groups will be conducted regularly to design out issues of concern, the EA Team will be engaged regularly for design feedback, and an EA plan will be prepared as part of the project. | 3 | 7 | Low
R10 | Requirement to keep the ability for resilience/flexibility through the area in traffic terms restricts the options that can be developed. | Planning | Operational | Unknown | Seek to ensure that an appropriate level of resilience is allowed for when designing Moorgate junctions at London Wall and Ropemaker Street. | 5 | 7 | Med