## Sheet1
Risk ID | Risk Description | Project Stage | Project Category | Risk Owner | Mitigating Action | Likelihood (1-10) | Impact (1-10) | Risk Priority (low, med, high)
R7 | The Council's ability to cope with a natural disaster, or a malicious or accidental incident that affects support required by civilians or disrupts existing Council services. | Operational | Operational | CMT | Key senior staff attend regular multi-agency briefing and planning meetings; Service Management Team conducts periodic exercises; recovery training is delivered and expanded; emergency plans are updated; volunteer rest centre staff are increased and trained; leisure centres are retained as rest centre sites; an officer on-call rota is implemented. | 4 | 8 | High
R4 | Failure to secure and manage data leads to loss, corruption, or inaccuracy of data, resulting in service disruption and security breaches, with potential financial penalties and reputational damage. | Operational | Operational | Unknown | An additional internet feed has been installed to improve resilience, data is backed up securely off-site, regular penetration testing is conducted, internet and email protocols have been updated, and disaster recovery testing is undertaken at regular intervals. | 5 | 8 | High
6 | Breach of ICT security from major IT hardware failure or electronic attack causes disruption to services and loss of data, with potential financial penalties and reputational damage. | Operational | Technical | Unknown | The Council subscribes to the NCSC Web Check service for regular website security scans, maintains off-site data backups, a tested disaster recovery plan, and updates software and security policies to address vulnerabilities. | 5 | 8 | High
17 | The risk is that legislative and political changes, particularly due to the ongoing Brexit transition process, may lead to immediate shifts in national priorities that require additional resources and could conflict with locally determined priorities. | Unknown | Legislation | Unknown | Monitor legislative changes via LGA, CIPFA, and other sources; implement clear corporate planning and resource allocation; conduct horizon scanning and collaborative working to respond to national policy shifts. | 4 | 7 | High
R3 | Failure of processes, contractors, and suppliers working on the Council’s behalf leads to additional costs or failed objectives due to inability to deliver services or meet agreed performance objectives. | Operational | Operational | Procurement CMT | Regular monitoring of contracts and performance, ensuring contracts include risk mitigation and contingency plans, and maintaining trained staff and business continuity plans to manage contractor or supplier failure. | 4 | 4 | Med
R10 | Major health and safety incident at Council leads to costs for inquiry, disruption to service and possible prosecution. | Operational | Health & Safety | CMT | Ensure health and safety is standard on all team meetings, maintain updated equipment inventories and inspections, conduct H&S audits in all services, and provide targeted refresher training and flu jabs for employees. | 4 | 4 | High
R16 | Service provision and performance are affected by organizational change, industrial action, and/or staff sickness, resulting in complaints, poor performance, and possible further costs. | Operational | Operational | Unknown | Business continuity plans are regularly checked and tested, and all services have up-to-date plans in place. Additionally, a comprehensive health and wellbeing programme supports staff through occupational health services, an employee assistance programme, and other initiatives. | 4 | 5 | Low
R1 | Legislative changes from Central Government or EU requiring significant organizational alterations, such as welfare reform and universal credit, risk GDPR breaches and ICO sanctions. | Operational | Legislation | GDPR Officer | Monitoring and horizon-scanning for legislative changes, ensuring staff training and updated procedures, using professional networking to identify best practices, responding to government consultations, and implementing detailed project plans for change. | 5 | 5 | High
R2 | Uncertainty during the transition period after the UK leaves the EU, followed by potential legislative, funding, and policy changes, may adversely affect the Council and its ability to provide services. | Planning | Legislation | Unknown | The Council continues to monitor progress and take account of any effects on local government as they emerge, and is actively preparing through its Corporate Brexit Project group, participation in the Cambridge and Peterborough Local Resilience Forum and Cambridgeshire Public Service Board, workforce reviews, and community signposting. | 3 | 3 | High
R8 | Risk of Council funding becoming unsustainable due to economic changes, imposed savings requirements, changes to local government funding systems, and uncertainties of pilot pension fund, leading to financial management decisions that make the Council's funding unsustainable. | Unknown | Financial | Finance Officer | The Council will closely monitor local government finance, maintain its Medium Term Financial Plan, implement an agreed Commercialisation and Investment Strategy, require services to identify transformation opportunities, and engage in shared services and lobbying through national working groups. | 5 | 5 | High
11 | Risk of fraud, corruption, malpractice, or error by internal or external threats, leading to financial loss, reputational harm, and additional costs. | Operational | Operational | Carol Pilson | The action plan includes increasing staff vigilance, providing fraud awareness training for managers, raising the profile of anti-fraud efforts internally and externally, reviewing and updating ICT systems for better protection, and continuing work with the Anglia Revenues Partnership fraud team and the National Fraud Initiative. | 4 | 7 | High
13 | Failure of governance models in major partners or within the Council, leading to unachieved priorities and poor performance by partner agencies. | Operational | Governance | Unknown | Assurance that the Annual Governance Statement reported to the Corporate Governance Committee shows the Council is in a strong governance position, supported by annual scrutiny of ARP and Planning, internal audit of partnership arrangements, and ensuring robust business continuity plans, GDPR compliance, and ICT processes are in place for all partners. | 5 | 5 | Med
R14 | Failure to achieve required savings targets, including delivering savings planned for in the Council’s annual budget and medium term financial strategy, resulting in greater than budgeted costs and potential risk of the Council not being able to set a balanced budget. | Operational | Financial | CMT | Implement robust controls for delivery of Council efficiency targets, including regular progress reports to Cabinet, service assurance to Members, and implementation of Procurement Strategy, Corporate Plan, and actions to increase income streams. | 5 | 9 | High
18 | The Council faces a financial risk from capital funding shortfalls, potentially leading to an increased burden if projected receipts from asset disposals or external funding are not realized or are delayed, which could require revisiting the capital programme to ensure sufficient funding. | Planning | Financial | Corporate Asset Team | Regularly review the capital funding programme and asset disposal strategy, monitor site valuations and market conditions, and pursue additional funding opportunities to ensure sufficient capital resources. | 5 | 7 | High
19 | Poor communication with stakeholders and staff leads to poorly informed direction of resources, lack of support for change, reputational damage, increased staff turnover, and sickness absence. | Unknown | Operational | Chief Executive | The Council has a dedicated project team to ensure ongoing progress against CSE requirements across all service areas, and all change projects are supported by a robust project management approach that includes a communication programme to ensure stakeholders are fully informed. | 3 | 5 | Med
R20 | Uncertainties associated with decisions taken as part of the Council’s Commercial and Investment Strategy could lead to reputational damage, financial loss, and impacts on services, staff, and community. | Unknown | Operational | Unknown | The Council will closely monitor this new risk to identify and implement any necessary additional mitigation actions, while maintaining robust governance, budget management, and project oversight. | 5 | 9 | Med
12 | Risk of failure of external investment institutions affecting availability of funds or return on investment, reducing cash flow and resource availability. | Operational | Financial | Treasury Management | The Council regularly reviews its treasury management position, conducts robust auditing of processes and policies, and provides half-yearly updates to Cabinet and Council. | 4 | 5 | Med
R5 | Insufficient staff and insufficient leadership and/or management capacity to deliver Council priorities, leading to poor standards of service or disruption to service, and potentially a loss of qualified staff which exposes the council to service failure and legal challenge. | Unknown | Operational | Learning & Development | Ensure all services have published service plans, learning requirements, and workforce plans for 2019-20 to staff teams according to establishment and priorities, and implement effective succession planning, flexible working, people policies, business continuity, project management approaches, staff development, and governance structures. | 5 | 8 | High
R7 | Lack of access to security systems and Council premises prevents services from being delivered, causing disruption of service provision. | Operational | Operational | Unknown | Regularly test emergency plans, conduct fire drills, test business continuity plans, ensure key emergency planning staff attend liaison meetings and training, and provide 'drop down' facilities for staff. | 5 | 7 | High
15 | Failure to manage projects effectively leads to overruns on time or cost and failure to achieve project aims, resulting in reputational damage. | Unknown | Planning | Project CMT | Implement robust project management, adhere to Contract Standing Orders & Financial Regulations, maintain effective risk registers, and ensure oversight by CMT and Portfolio Holders with regular progress reporting to Council. | 4 | 5 | Med
R1 | Legislative changes could impact the Council's operations and service delivery. | Unknown | Legislation | Unknown | The action plan is not explicitly stated in the provided risk text. | 5 | 5 | High