## Sheet1
Risk ID | Risk Description | Project Stage | Project Category | Risk Owner | Mitigating Action | Likelihood (1-10) | Impact (1-10) | Risk Priority (low, med, high)
R1 | Opening of the Moorgate Crossrail station is delayed further. | Commissioning | Planning | Unknown | Regular engagement with Crossrail from now to 2020/2021 to allow for alternative arrangements should there be a delay in delivery. | 5 | 3 | Low
R2 | The Riney highways contract expires in summer 2022, and any slippage in starting construction could require appointing a new Principal Contractor for later stages. | Pre-construction | Procurement | Unknown | Conduct internal discussions if the risk becomes more probable to determine how work might be transferred to a new contractor or alternative arrangements. | 3 | 3 | Low
R3 | Delays to the four developments surrounding the Moorgate Crossrail station could delay the final delivery phases of the MCSL project. | Construction | Planning | Unknown | Regular engagement with developers to ensure early detection of delays and facilitate alternative arrangements. | 5 | 7 | Med
R4 | Infrastructure and utilities difficulties at the Moorgate junction with London Wall and with Ropermaker Street, make it difficult/too expensive to design and transform the space, as well as enhance safety. | Pre-construction | Design | Unknown | Set expectations at the earliest stage possible where it is discovered that there are major physical constraints. Work closely with internal and external stakeholders to identify design solutions to bring the work forward that might not require such extensive physical changes. | 5 | 8 | Med
R5 | Key stakeholder(s) do not endorse design options | Pre-construction | Planning | Unknown | Ensure that Stakeholder Working Group is suitably engaged. | 5 | 7 | Med
R6 | Delays/changes to dependency projects, such as Beech Street and St. Paul's Gyratory. | Pre-construction | Programme | Unknown | Work with internal stakeholders to minimize any impacts should changes arise. | 5 | 7 | Med
R7 | Breakdown in engagement with key stakeholders, such as Islington Council. | Pre-construction | Planning | Unknown | Ensure coherent communications with stakeholders and ensure stakeholders are communicated with at strategic points throughout the project, particularly regarding proposed boundary solutions. | 3 | 7 | Low
R8 | TfL restructure may mean that no dedicated scheme sponsor / resource can be allocated to progress any required TfL approvals. | Pre-construction | Legislation | Unknown | Officers will seek to establish resources as early as possible and keep close contact to understand the extent of the restructure, seeking reassurance of resource if needed. | 7 | 8 | High
R9 | There is a potential that the proposed scheme could impact negatively on the protected characteristics under the Equalities Act, 2010. | Pre-construction | Legislation | Unknown | Conduct regular meetings with representative groups and engage the EA Team for design feedback, while preparing an Equality Act plan. | 2 | 7 | Low
R10 | The requirement to maintain traffic resilience and flexibility in the area restricts development options for the Moorgate Crossrail Reasoner project. | Pre-construction | Design | Unknown | Seek to ensure that an appropriate level of resilience is allowed for when designing Moorgate junctions at London Wall and Ropemaker Street. | 5 | 7 | Med