## Sheet1
Risk ID | Risk Description | Project Stage | Project Category | Risk Owner | Mitigating Action | Likelihood (1-10) | Impact (1-10) | Risk Priority (low, med, high)
R1 | Opening of the Moorgate Crossrail station is delayed further. | Operation | Planning | Project Manager | Regular engagement with Crossrail from now to 2020/2021 to allow for alternative arrangements should there be a delay. | 4 | 1 | Low
R2 | The Riney highways contract is due to expire in the summer of 2022. Any slippage in starting the construction programme may mean we have to consider a new Principal Contractor for the later stages of delivery. | Construction | Procurement | Project Manager | Discussions to take place internally should this risk look more probable on how work would be transferred to a new contractor. | 3 | 3 | Low
R3 | Delays to the four developments surrounding the Moorgate Crossrail station delay the final delivery phases of the MCSL project. | Construction | Planning | Project Manager | Regular engagement with developers from now until completion of the developments to allow for alternative arrangements and early notification of any delays. | 5 | 7 | Med
R4 | Infrastructure and utilities difficulties at the Moorgate junction with London Wall and Ropermaker Street make it difficult or too expensive to design and transform the space and enhance safety. | Pre-construction | Infrastructure | Project Manager | Set expectations early regarding major physical constraints and collaborate with stakeholders to identify design solutions that minimize extensive physical changes. | 5 | 8 | Med
R5 | Key stakeholder(s) do not endorse design options | Pre-construction | Planning | Project Manager | Ensure that Stakeholder Working Group is suitably engaged and that design options are presented and discussed with key stakeholders to secure endorsement. | 5 | 7 | Med
R6 | Delays/changes to dependency projects, such as Beech Street and St. Paul's Gyratory. | Construction | Planning | Project Manager | Work with internal stakeholders to minimize any impacts should changes arise. | 5 | 7 | Med
R7 | Breakdown in engagement with key stakeholders, such as Islington Council. | Pre-construction | Planning | Project Manager | Ensure coherent communications with stakeholders at strategic points throughout the project, particularly regarding proposed boundary solutions. | 3 | 7 | Low
R8 | TfL restructure may mean that no dedicated scheme sponsor / resource can be allocated to progress any required TfL approvals. | Pre-construction | Planning | Project Manager | Officers will seek to establish resources as early as possible and keep close contact to understand the extent of the restructure, seeking reassurance of resource if needed. | 8 | 8 | High
R9 | The proposed scheme could negatively impact protected characteristics under the Equalities Act 2010. | Pre-construction | Regulations | Unknown | Meetings with representative groups will be conducted regularly to design out issues of concern, and an EA plan will be prepared. | 3 | 7 | Low
R10 | Requirement to keep the ability for resilience/flexibility through the area in traffic terms, restricts the options that can be developed. | Pre-construction | Planning | Project Manager | Seek to ensure that an appropriate level of resilience is allowed for when designing Moorgate junctions at London Wall and Ropemaker Street. | 5 | 7 | Med